## Project Plan Template (hidden)
PROJECT PLAN TEMPLATE
| PROJECT TITLE |  | START DATE
|  |  | 2024-01-02 |  |  | PROJECT DURATION
| PROJECT MANAGER |  | END DATE |  |  | in days
|  |  | 2024-03-26 |  |  | 85
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION | Complete |  | 2024-01-02 | 2024-02-09 | 39 |  | Not Started
1.1 | – Project Charter | Complete |  | 2024-01-02 | 2024-01-11 | 10 |  | In Progress
1.1.1 | –– Project Charter Revisions | Complete |  | 2024-01-07 | 2024-01-11 | 5 |  | Complete
1.2 | – Research | Complete |  | 2024-01-10 | 2024-02-23 | 45 |  | On Hold
1.3 | – Projections | Complete |  | 2024-01-10 | 2024-01-20 | 11
1.4 | – Stakeholders | Complete |  | 2024-01-16 | 2024-01-29 | 14
1.5 | – Guidelines | In Progress |  | 2024-01-19 | 2024-02-01 | 14
1.6 | – Project Initiation | In Progress |  | 2024-01-22 | 2024-02-09 | 19
2 | PROJECT DEFINITION AND PLANNING | In Progress |  | 2024-01-28 | 2024-02-14 | 18
2.1 | – Scope & Goal Setting | On Hold |  | 2024-01-28 | 2024-02-06 | 10
2.2 | – Budget | In Progress |  | 2024-01-31 | 2024-02-02 | 3
2.3 | – Communication Plan | In Progress |  | 2024-02-04 | 2024-02-12 | 9
2.4 | – Risk Management | Complete |  | 2024-02-06 | 2024-02-14 | 9
3 | PROJECT LAUNCH & EXECUTION | Complete |  | 2024-02-18 | 2024-03-26 | 38
3.1 | – Status & Tracking | In Progress |  | 2024-02-18 | 2024-02-20 | 3
3.2 | – KPIs | In Progress |  | 2024-02-18 | 2024-02-23 | 6
3.2.1 | –– Monitoring | In Progress |  | 2024-02-18 | 2024-02-26 | 9
3.2.2 | –– Forecasts | Not Started |  | 2024-02-21 | 2024-02-23 | 3
3.3 | – Project Updates | Not Started |  | 2024-02-22 | 2024-02-23 | 2
3.3.1 | –– Chart Updates | In Progress |  | 2024-02-25 | 2024-03-26 | 31
4 | PROJECT PERFORMANCE / MONITORING | In Progress |  | 2024-02-25 | 2024-03-26 | 31
4.1 | – Project Objectives | In Progress |  | 2024-02-25 | 2024-02-28 | 4
4.2 | – Quality Deliverables | On Hold |  | 2024-02-26 | 2024-03-03 | 7
4.3 | – Effort & Cost Tracking | Not Started |  | 2024-02-25 | 2024-03-06 | 11
4.4 | – Project Performance | Not Started |  | 2024-03-03 | 2024-03-26 | 24
CLICK HERE TO CREATE IN SMARTSHEET

## Capstone Project Plan
PROJECT PLAN TEMPLATE
| PROJECT TITLE |  | START DATE
| Cloud Migration |  | 2022-01-15 |  |  | PROJECT DURATION
| PROJECT LEAD & TEAM |  |  |  |  | in days
| Team - Anjali Kumari, Kanan Ganach, Nitika Gupta, Thanh Trung Nguyen Lead - Nitika Gupta |  | 2022-04-09 |  |  | 85
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION |  |  |  |  | 1 |  | Not Started
1.1 | – Project Ideas | Complete | Team | 2022-01-15 | 2022-01-28 | 14 |  | In Progress
1.1.1 | –– Brainstorming sessions | Complete | Team | 2022-01-17 | 2022-01-20 | 4 |  | Complete
1.2 | – Research | In Progress | Team | 2022-01-17 | 2022-01-24 | 8 |  | On Hold
1.3 | – Scenario Ideation | In Progress | Team | 2022-01-24 | 2022-01-24 | 1
1.4 | – High Level Requirements | In Progress | Team |  |  | 1
1.5 | – Guidelines |  |  |  |  | 1
1.6 | – Project Initiation |  |  |  |  | 1
2 | PROPOSED PLAN AND SOLUTION |  |  |  |  | 1
2.1 | – Scope & Goal Setting |  |  |  |  | 1
2.2 | – Budget |  |  |  |  | 1
2.3 | – Communication Plan |  |  |  |  | 1
2.4 | – Risk Management |  |  |  |  | 1
3 | BUILDBOOK & WORK INSTRUCTIONS |  |  |  |  | 1
3.1 | – Status & Tracking |  |  |  |  | 1
3.2 | – KPIs |  |  |  |  | 1
3.2.1 | –– Monitoring |  |  |  |  | 1
3.2.2 | –– Forecasts |  |  |  |  | 1
3.3 | – Project Updates |  |  |  |  | 1
3.3.1 | –– Chart Updates |  |  |  |  | 1
4 | FINAL PROJECT SUBMISSION - LAB CONFIGURATION |  |  |  |  | 1
4.1 | – Project Objectives |  |  |  |  | 1
4.2 | – Quality Deliverables |  |  |  |  | 1
4.3 | – Effort & Cost Tracking |  |  |  |  | 1
4.4 | – Project Performance |  |  |  |  | 1
5 | FINAL PROJECT PRESENTATION
4.1 | – Project Objectives |  |  |  |  | 1
4.2 | – Quality Deliverables |  |  |  |  | 1
4.3 | – Effort & Cost Tracking |  |  |  |  | 1
4.4 | – Project Performance |  |  |  |  | 1
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Scenario
Scenario

## -Disclaimer- (hidden)
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.